## Sheet 1 - Work Breakdown Struct
Work Breakdown Structure
Task | Assigned To | Planned Start | Planned End | Predecessor | Percent Complete
Develop Front End Rapid Prototype | Team | 2019-02-13 | 2019-02-15 | — | 100%
Database Design | Zane | 2019-02-21 | 2019-03-07 | — | 100%
Abstract Class Implementation | Xiaotang | 2019-02-17 | 2019-03-07 | — | 100%
— Redesign Object Hierarchy | Alyssa | 2019-02-28 | 2019-03-07 | — | 100%
— Formula Design | Tyler | 2019-02-28 | 2019-03-07 | Object Hierarchy | 100%
— Formula Implementation | Alyssa and Zane | 2019-02-28 | 2019-03-07 | Formula Design | 100%
Upload WBS, RASCI, ERD, and Project Plan | Alyssa | 2019-02-28 | 2019-02-28 | — | 100%
Frontend Implementation | Farid | 2019-02-21 | 2019-03-07 | — | 100%
— Implement Localization | Tyler | 2019-03-24 | 2019-04-05 | — | 100%
— Bug Fixes | Farid | 2019-03-24 | 2019-04-05 | — | 100%%
— Graphical Representation | Farid and Zane | 2019-03-24 | 2019-04-05 | — | 100%
Create Final Presentation Slides | Team | 2019-04-04 | 2019-04-09 | — | 100%
Create Post Project Review Slides | Team | 2019-04-09 | 2019-04-11 | — | 100%
Project Presentation | Team | 2019-04-12 | — | Everything
Post Project Presentation | Team | 2019-04-19 | — | Everything